## Test Cases
AIVOA.AI — Manual Testing Document
Tester: samiksha ¦ Date: 20-05-2026 ¦ Browser: Chrome ¦ Device: Windows 11
TC ID | Module / Area | Test Case Description | Pre-condition | Test Steps | Expected Result | Actual Result | Status | Bug Severity | Remarks / Notes
▶ HOMEPAGE & NAVIGATION
TC-001 | Homepage | Homepage loads successfully within 3 seconds | Browser open | 1. Open https://aivoa.ai/ 2. Note load time | Page loads fully, no broken elements, load ≤3s | Homepage loaded successfully within 3 seconds without any broken elements. | Pass | N/A | Homepage loaded successfully without issues
TC-002 | Homepage | Page title & favicon are correct | Homepage loaded | 1. Check browser tab title 2. Check favicon icon | Title = 'AIVOA.QMS.AI', favicon visible | Browser tab displays “QMS.AIVOA.AI” title and favicon/logo is visible correctly. | Pass | N/A | Working as expected
TC-003 | Navigation | All navbar links are clickable & navigate correctly | Homepage loaded | 1. Click each nav link one by one 2. Note destination URL | Each link goes to correct section/page, no 404 | All navbar links are clickable and navigate to correct pages/sections. No 404 error observed.” | Pass | N/A | “All navigation links are working as expected.”
TC-004 | Navigation | Logo click redirects to homepage | Any inner page | 1. Click on AIVOA logo 2. Check URL | Redirected to https://aivoa.ai/ | Clicking the AIVOA logo does not redirect to homepage. No action is performed. | Fail | Low | Logo is not clickable / homepage navigation not working.
TC-005 | Navigation | Mobile hamburger menu works | Open on mobile/375px | 1. Resize to mobile 2. Click hamburger icon 3. Click menu items | Menu opens/closes, all links work on mobile | Hamburger menu opens, but navigation links (Why AI?, Platform, How It Works, Modules, Case Studies, Pricing, Contact Us) are not clickable / not opening pages on mobile view. | Fail | Medium | Mobile navigation links are not working properly at 375px screen size
TC-006 | Scroll | Smooth scroll / anchor links work | Homepage loaded | 1. Click any 'Learn More' / anchor CTA 2. Observe scroll behaviour | Page scrolls smoothly to target section | Smooth scroll works. Modules section shows interactive product demos for each module — Quality Events, Docs, Training etc. Red underline indicates active/selected module | Pass | N/A | Modules section intentionally auto-scrolls through live product demos — this is a feature, not a bug
▶ CTA BUTTONS & LINKS
TC-007 | CTA Button | Primary CTA button is visible above the fold | Homepage loaded | 1. Check hero section 2. Look for main CTA button | CTA button visible, text readable, clickable | Both CTA buttons ‘Book a Free Demo’ and ‘Watch Demo’ are visible above the fold on the homepage. On clicking both buttons, respective pages are opened successfully without any issue | Pass | N/A | “Primary CTA buttons are working as expected and navigation is correct.”
TC-008 | CTA Button | CTA button hover state works | Homepage loaded | 1. Hover over CTA button 2. Check visual change | Button shows hover effect (color/shadow change) | On hovering over the CTA button, visual change is observed (color/shadow change), and hover state works as expected.” | Pass | N/A | “Hover state is working correctly for CTA button.”
TC-009 | CTA Button | CTA click leads to correct page/form | Homepage loaded | 1. Click primary CTA button 2. Note destination | Correct landing page/Book a Free Demo form opens | Both CTA buttons work correctly — "Book a Free Demo" opens demo booking popup form, "Watch Demo" opens correct destination | Pass | N/A | All CTA buttons lead to correct pages/forms
TC-010 | Links | No broken links (404) on the page | Homepage loaded | 1. Click every hyperlink 2. Note any 404 errors | All links return 200 OK, no 404/500 errors | “All navbar links are clickable and redirect to their respective correct pages/sections without any errors.” | Pass | N/A | “No broken links observed. All links are working as expected and navigation is correct.”
TC-011 | Links | External links open in new tab | Homepage loaded | 1. Click any external link 2. Check if new tab opens | New tab opens, original tab stays | External links (LinkedIn, Twitter, YouTube) are opening in a new tab as expected. However, Twitter link redirects to a page showing ‘This account doesn’t exist’ message.” and YouTube link redirects to a 404 error page (‘This page isn’t available’) | Fail | Medium | “LinkedIn and Twitter links are working correctly in new tabs. However, YouTube external link is broken and redirects to a 404 error page. This needs to be fixed.”“External links are opening in new tab successfully. and However, Twitter link is pointing to an inactive or incorrect account (‘This account doesn’t exist’), which needs to be corrected.”
▶ FORMS & VALIDATIONS
TC-012 | Book a Demo Form | Demo form renders correctly | Homepage loaded | 1. Click 'Book a Demo' button 2. Check all form fields visible | All fields visible: Work Email, Name, Phone, Company, Industry Type, Submit | Form opens in popup with: Work Email*, Your Name*, WhatsApp/Phone, Company Name*, Biggest QA Headache dropdown, Industry Type checkboxes, Submit button | Pass | N/A | All form fields visible and functional. Form accessible via Book a Demo popup only — not in Contact Us section.
TC-013 | Book a Demo Form | Submit with all empty fields | Demo form open | 1. Leave all fields empty 2. Click Submit | Validation errors shown for required fields | Validation error shown on Work Email field: "Fill out this field" | Pass | N/A | Browser default HTML5 validation working. Required field validation triggers on submit
TC-014 | Book a Demo Form | Invalid email format rejected | Demo form open | 1. Enter 'abc' in Work Email 2. Click Submit | Error: Please enter valid email address | Error shown: "Please include an '@' in the email address. 'abc' is missing an '@'" | Pass | N/A | Browser HTML5 email validation working correctly
TC-015 | Book a Demo Form | Valid email format accepted | Demo form open | 1. Enter 'test@gmail.com' 2. Click Submit | No email validation error | Valid email accepted, no email error. Next required field (Name) validation triggered showing "Fill out this field" | Pass | N/A | Email validation working correctly. Form moves to next required field validation
TC-016 | Book a Demo Form | Name field: only spaces rejected | Demo form open | 1. Enter ' ' spaces in Name 2. Click Submit | Error shown, blank name not accepted | Spaces accepted in Name field — no validation error shown. Form proceeded to Company Name field validation | Fail | Medium | Name field accepts blank spaces as valid input — whitespace validation missing
TC-017 | Book a Demo Form | Successful form submission message | Demo form open | 1. Fill all fields correctly 2. Click Submit | Success message shown | Success message shown: "Demo booked! Thanks — our team will reach out shortly to confirm your slot" | Pass | N/A | Form submits successfully, confirmation message clear and professional
TC-018 | Book a Demo Form | Long text input in name/email box | Demo form open | 1. Paste 2000+ characters 2. Click Submit | Form handles gracefully, no crash | No crash on long text input. Form handled gracefully, moved to next required field validation (Company Name) | Pass | N/A | Form stable with 2000+ character input, no crash or freeze
TC-019 | Book a Demo Form | SQL injection in input fields | Demo form open | 1. Enter: ' OR 1=1; -- in name 2. Submit | Form rejects or sanitizes, no server error | SQL injection input accepted in Name field — no error, no crash. Form proceeded to Company Name validation | Pass | N/A | Form handled SQL injection gracefully — no server error or crash. Frontend accepts input, backend validation assumed
TC-020 | Book a Demo Form | XSS in input fields | Demo form open | 1. Enter: <script>alert(1)</script> 2. Submit | Script not executed, input sanitized | XSS script entered in Name field — no alert popup executed. Form showed normal validation error for Company Name field | Pass | N/A | XSS input sanitized correctly — script tag not executed, no security vulnerability found
▶ UI / UX & VISUAL
TC-021 | UI | No overlapping text or elements | Homepage loaded | 1. Scroll entire page 2. Check for overlaps | All elements properly spaced, no overlap | “The homepage UI is well structured and most elements are properly aligned. However, on scrolling the page, some sections (CTA area / hero content overlap in smaller view) show slight layout crowding in certain viewport positions, but no major element blocking observed.” | Pass | N/A | Overall UI is visually stable and no critical overlapping of elements observed. Minor spacing adjustments may be needed in some sections for better responsiveness.”
TC-022 | UI | Images load without broken icon | Homepage loaded | 1. Scroll entire page 2. Check all images | All images load, no broken image icons | All images on the homepage load successfully while scrolling the page. No broken image icons or missing images are observed | Pass | N/A | All images are loading properly without any broken or missing image icons. UI images are displayed correctly across the page.
TC-023 | UI | Font consistency across sections | Homepage loaded | 1. Compare fonts in Navbar, Hero, Body, Footer | Consistent font family & sizing throughout | Font family across Navbar, Hero section, body content, and footer appears consistent. However, minor variation in font size/weight is observed between some headings and body text, but overall font style remains uniform | Pass | N/A | Overall font family is consistent across all sections. Minor differences in font sizing/weight observed in headings, but no major inconsistency affecting UI readability.”
TC-024 | UI | Color contrast is readable (WCAG) | Homepage loaded | 1. Check text on colored backgrounds | Text readable, contrast ratio ≥ 4.5:1 | Lighthouse Accessibility score: 95/100. Contrast issue found: "Background and foreground colors do not have sufficient contrast ratio" | Fail | Medium | WCAG contrast ratio requirement not met for some elements — Lighthouse flagged contrast issue
TC-025 | UI | Footer content is complete | Scroll to bottom | 1. Check footer links, copyright, socials | Footer has copyright, links, social icons | Footer present with copyright © 2026, nav links (Platform, Resources, Company), social icons. But YouTube and Twitter/X links broken | Partial Pass | Medium | Footer content complete but 2 social links broken (already logged as BUG-008, BUG-009)
TC-026 | Responsive | Desktop layout (1920×1080) | Browser open | 1. Set to 1920×1080 2. Check layout | Layout fills correctly, no excessive whitespace | Desktop layout renders correctly at 1920×1080. No excessive whitespace, elements properly aligned | Pass | N/A | Layout fills screen correctly on desktop resolution
TC-027 | Responsive | Tablet layout (768×1024) | Browser open | 1. Set to 768×1024 2. Check layout | Elements reflow correctly, readable | Tablet layout renders correctly at 768×1024. Content readable, no horizontal scroll. Navbar condensed to show only Contact Us and Book a Demo — other nav links hidden | Partial Pass | Medium | Layout works but nav links (Why AI, Platform, Modules etc.) not visible on tablet — no hamburger menu found
TC-028 | Responsive | Mobile layout (375×812) | Browser open | 1. Set to 375×812 2. Check layout | No horizontal scroll, all text readable | Mobile layout loads at 375×812. Content reflows but text gets cut off in hero section. No hamburger menu — navigation links completely missing on mobile | Fail | High | Text truncated in hero description, stats section cut off. Navigation menu missing on mobile view
▶ PERFORMANCE & CROSS-BROWSER
TC-029 | Performance | Page load on Chrome | Chrome browser | 1. Open aivoa.ai in Chrome 2. Check DevTools → Network tab | Page loads < 5s, no console errors | Page load time 23.2 min, 0/69 requests completed, 23.5MB data stuck | Fail | Critical | Page completely fails to load. 69 requests stuck, 23MB unloaded. Site practically unusable.
TC-030 | Performance | Page load on Firefox | Firefox browser | 1. Open aivoa.ai in Firefox 2. Check load time | Page loads correctly in Firefox | Page loads in 1.52s on Firefox, 18/18 requests completed, 5.68MB transferred | Pass | N/A | Excellent load on Firefox. But same site fails on Chrome (23 min) — cross-browser issue
TC-031 | Performance | No console JS errors | Chrome DevTools | 1. Press F12 → Console 2. Reload page 3. Check for errors | Zero red errors in console | Result2 console errors + 11 DevTools issues found. Form fields missing id/name attributes (5 resources affected), form fields have no labels | Fail | Medium | JS promise error + form accessibility issues detected
TC-032 | Performance | HTTPS & SSL certificate valid | Browser address bar | 1. Check padlock icon 2. Click padlock → Certificate | Valid SSL, no security warning | Valid SSL certificate found. Issued by Let's Encrypt, valid from 14 May 2026 to 12 Aug 2026 | Pass | N/A | HTTPS active, certificate valid for 83 more days
▶ CONTENT & SEO
TC-033 | Content | No spelling / grammar errors | Homepage loaded | 1. Read all visible text carefully | Zero spelling/grammar mistakes | ResultGrammarly detected 50 suggestions. Key issues: missing spaces between words (AmnesiaRecurring, DetectionAI, PlanningAI, AlokDue), spelling errors (analyzes), redundant words | Fail | Medium | Overall score 80/100. Multiple words merged without spaces across content sections
TC-034 | Content | Meta description present | DevTools | 1. Right click → View Page Source 2. Search <meta name='description'> | Meta description tag exists and is meaningful | ResultMeta description found in page source: "AIVOA is the next-generation, AI-native QMS for Life Sciences..." | Pass | N/A | Meta description present and meaningful. Note: Tag visible in view-source but not in DevTools Elements (React SPA rendering)
TC-035 | Content | Social media links work | Footer | 1. Click LinkedIn/Twitter/social icons 2. Check destination | Correct social page opens in new tab | ResultYouTube: page not available. Twitter/X: account doesn't exist. LinkedIn: page opens and proper work | Fail | High | 2 out of 3 social links broken. Only LinkedIn works

## Bug Report
AIVOA.AI — Bug Report Log
Bug ID | TC ID Ref | Bug Title | Module | Severity | Steps to Reproduce | Expected | Actual | Status
BUG-001 | TC-029 | Chrome page load fails — 23+ min load time | Performance | Critical | 1. Open Chrome 2. Go to aivoa.ai 3. F12 → Network 4. Disable cache 5. Ctrl+Shift+R | Page loads under 5 seconds | Page takes 23.2 min, 0/69 requests, 23.5MB not transferred | Open
BUG-002 | TC-029,TC-030 | Cross-browser issue — Chrome fails, Firefox works | Performance | Critical | 1. Open aivoa.ai Chrome → 23 min load 2. Open Firefox → 1.52s load | Consistent load time across all browsers | Firefox=1.52s ✅ Chrome=23min ❌ — 65% users use Chrome | Open
BUG-003 | TC-031 | Form fields missing id/name — 5 resources affected | Forms/Accessibility | Medium | F12 → Issues tab → 'Form field should have id or name' | All form fields have proper id and name | 5 form fields missing id/name — autofill broken | Open
BUG-004 | TC-031 | Form fields have no associated labels | Forms/Accessibility | Medium | F12 → Issues tab → 'No label associated with form field' | Every form field has visible label | Form fields missing labels — screen readers fail | Open
BUG-005 | TC-032 | SSL is DV certificate only — Organization not verified | Security | Low | Click padlock → Certificate → Check Organization | OV/EV SSL for pharma-grade software | Only Domain Validated (DV) SSL — Organization field empty | Open
BUG-006 | TC-033 | 50 spelling/grammar issues — Grammarly score 80/100 | Content | Medium | Copy website text → Paste in Grammarly | Zero errors, score 95+ | 50 issues: AmnesiaRecurring, DetectionAI (missing spaces), analyzes (spelling) | Open
BUG-007 | TC-034 | Single meta description for entire SPA | SEO | Low | view-source:https://aivoa.ai/ → Check meta tags | Each page has unique meta description | Only one global meta — bad SEO for multi-section SPA | Open
BUG-008 | TC-035 | YouTube link broken — Page not available | Social Media | High | Scroll to footer → Click YouTube icon | AIVOA YouTube channel opens | youtube.com/@aivoa_ai — This page isn't available (404) | Open
BUG-009 | TC-035 | Twitter/X link broken — Account doesn't exist | Social Media | High | Scroll to footer → Click Twitter/X icon | AIVOA Twitter/X page opens | x.com/aivoa_ai — This account doesn't exist | Open
BUG-010 | TC-031 | Console JS error — Uncaught Promise Error | Performance | Medium | F12 → Console tab → Reload page | Zero red errors in console | Uncaught (in promise) Error: message channel closed | Open
BUG-011 | TC-012 | Contact form missing from Contact Us section | UX/Forms | Medium | Click 'Contact Us' in navbar | Contact form with input fields | Only static info — form only in Book a Demo popup | Open
BUG-012 | TC-016 | Name field accepts blank spaces — no whitespace validation | Forms | Medium | 1. Book a Demo 2. Enter spaces in Name 3. Submit | Error: Please enter valid name | Spaces accepted, no validation error | Open
BUG-013 | TC-024 | Insufficient color contrast — WCAG AA fail | UI/Accessibility | Medium | F12 → Lighthouse → Accessibility → Contrast | Contrast ratio ≥ 4.5:1, score 100 | Score 95/100 — contrast issue flagged | Open
BUG-014 | TC-004 | Logo click not working — no homepage redirect | Navigation | Low | 1. Go to inner page 2. Click AIVOA logo | Logo redirects to homepage | Logo click performs no action | Open
BUG-015 | TC-028 | Text cut off in hero section on mobile 375px | Responsive | High | F12 → Toggle Device → 375x812 → Hero section | Full text visible, no truncation | Hero description & stats cut off on right side | Open
BUG-016 | TC-005,TC-028 | No hamburger menu on mobile — nav links missing | Responsive | High | F12 → Toggle Device → 375x812 → Check navbar | Hamburger menu with all nav links | Only Contact Us + Book a Demo visible, no hamburger | Open

## Summary
Test Execution Summary
Tester Name | Samiksha
Website URL | https://aivoa.ai/
Test Date | 21 May 2026
Browser & Version | Chrome 124 + Firefox 125
Device / OS | Windows 11, Laptop
RESULTS
Total Test Cases | 35
Pass | 22
Fail | 9
Skip / Not Tested | 2
BUG SUMMARY
Critical Bugs | 2
High Bugs | 4
Medium Bugs | 7
Low Bugs | 3
Total Bugs Found | 16
Overall Verdict | Website has critical Chrome performance issues. 16 bugs found. Core functionality works on Firefox. Needs urgent fixes before production launch.